## Project Schedule
PROJECT SCHEDULE TEMPLATE
PROJECT NAME | Shazamify Pi Music Recognition Bot
PROJECT DELIVERABLE | Full-featured music recognition device with custom hardware, advanced audio analysis, and touchscreen interface
SCOPE STATEMENT | Develop complete embedded system with Raspberry Pi integration, custom chassis, music recognition, advanced sound plotting, and polished touchscreen UI
START DATE | 2024-10-19 | OVERALL PROGRESS
|  | Software | 80%
|  | Hardware | 0%
TASK NAME | ASSIGNED TO | STATUS | COMMENTS
Core Development Kickoff | Team | Complete | Initial planning and architecture design
Setup MVC Architecture | Team | Complete | Refactored from single script to MVC pattern
UI Framework Setup | Benjamin I. | Complete | PyQt6 main window and tab structure
Audio Recording Module | Nate L. | Complete | PyAudio integration with configurable duration
Threading Implementation | Benjamin I. | Complete | QThread for non-blocking recording
FFT Processing Pipeline | Nate L. | Complete | NumPy FFT with magnitude spectrum
Plot Canvas Integration | Nate L. | Complete | Matplotlib embedded
Spotify API Client Setup | Omar P. | Complete | Authentication flow
Metadata Retrieval API | Omar P. | Complete | Search and track info methods
Check-In Meeting | Benjamin I. | Complete | Team sync and risk assessment
Album Artwork Display | Benjamin I. | Complete | Dynamic image loading from URLs
Plot-UI Signal Connection | Nate L. | Complete | Thread-safe plot updates
Duration Control Buttons | Benjamin I. / Omar P. | Complete | 3s, 5s, 10s recording options
Documentation Update | Nate L. | Complete | README and code comments updated
Recognition Bridge Completion | Omar P. | In Progress | Connect audio fingerprint to Spotify
Shazam API Integration | Omar P. | Planned | Implement Shazam recognition API
Recognition Accuracy Testing | Omar P. | Planned | Test with various music genres
Display Song/Artist/Album | Benjamin I. | Planned | Complete UI display integration
Similar Songs Feature | Omar P. | Planned | Fetch and display related tracks
Similar Artists Feature | Omar P. | Planned | Show related artists with images
Recognition Confidence Score | Benjamin I. | Planned | Display match percentage
Sonogram Implementation | Nate L. | Planned | Time-frequency spectrogram
Waterfall 3D Spectra | Nate L. | Planned | 3D visualization of spectrum evolution
Log-MEL Spectrogram | Nate L. | Planned | Perceptual frequency scaling
Chromagram Display | Nate L. | Planned | 12 pitch classes visualization
Tempogram Analysis | Nate L. | Planned | Tempo and rhythm visualization
Live Waveform Animation | Benjamin I. | Planned | Real-time waveform during recording
Tab Transitions / Other animations | Benjamin I. | Planned | Smooth animations between tabs/ Widget Animations/ Dark Mode Theme/ Custom Recording Timer
Recording History | Benjamin I. | Planned | List of previous recognitions/ recognitions
Raspberry Pi 4 Setup | Omar P. | Planned | OS installation and configuration
Pin Mapping | Nate L. | Planned | Define pin assignments for components
USB Audio Interface Setup | Nate L. | Planned | Configure external DAC/ADC
Physical Button Integration | Benjamin I. / Omar P. | Planned | Hardware buttons for record/stop
LED Status Indicators | Omar P. | Planned | RGB LED for system status
Power Management Circuit | Team | Planned | Battery and charging system
SolidWorks Model Creation | Omar P. / Nate L. | Planned | SolidWorks design
Ventilation Design | Omar P. / Nate L. | Planned | Thermal management slots
Component Layout Planning | Team | Planned | Internal space optimization
Material Selection | Omar P. / Nate L. | Planned | ABS vs PLA vs Aluminum analysis
3D Print Prototype | Omar P. / Nate L. | Planned | First chassis iteration
Mounting Points Design | Omar P. / Nate L. | Planned | Secure attachment for all components
Port Cutouts | Omar P. / Nate L. | Planned | USB, audio, power openings
Surface Finish Design | Team | Planned | Texture and color scheme
Software Port to Pi | Omar P. | Planned | Adapt code for ARM architecture
Driver Optimization | Nate L. | Planned | Audio latency reduction
Touchscreen Calibration | Benjamin I. | Planned | Touch accuracy adjustment
Assembly Documentation | Team | Planned | Step-by-step build guide
Full System Assembly | Team | Planned | Complete hardware build
Integration Testing | Team | Planned | Hardware-software validation
Performance Benchmarking | Team | Planned | Response time and accuracy metrics
Field Testing | Team | Planned | Real-world usage scenarios
Project Submission | Team | Planned | Final deliverables uploaded
**Planned Hardware Components List:**
COMPONENT | SPECIFICATION | SUPPLIER | COST
Raspberry Pi 4 | 8GB RAM Model B | Adafruit | 75
7" Touchscreen | Official Pi DSI Display | Raspberry Pi | 60
USB Audio Interface | Behringer UCA222 | Amazon | 30
Microphone | USB Condenser Mic | Amazon | 25
Power Supply | 5V 3A USB-C | CanaKit | 10
MicroSD Card | 64GB Class 10 | SanDisk | 15
Push Buttons | Momentary 12mm | Adafruit | 8
RGB LED | Common Cathode | Adafruit | 4
Mounting Hardware | M2.5 Standoff Kit | Amazon | 12
TOTAL HARDWARE BUDGET |  | 239